# PPS Executive Briefing Framework

Date: 2026-06-26

# Objective

This document defines the architecture of the PPS Executive Briefing.

The Executive Briefing becomes the primary landing page for every project and provides an executive-level understanding of project status without requiring navigation through operational tables.

The objective is to present the most important information on a single page while allowing seamless navigation to the detailed operational sections.

The Executive Briefing is not intended to replace operational pages. It complements them by providing a management-oriented view of the project.

# Design Philosophy

The Executive Briefing follows three principles.

The top of the page explains the project.

The middle of the page shows whether the project is under control.

The bottom of the page explains what management needs to do next.

The page is designed for rapid executive understanding rather than detailed project administration.

# General Principles

The Executive Briefing shall:

- Fit on a single page whenever practical.

- Avoid long scrolling.

- Organize information into clearly separated visual sections.

- Present information in a consistent reading order.

- Provide direct navigation to operational pages.

- Reuse existing project data rather than duplicate maintenance.

Each section shall answer exactly one executive question.

# Information Hierarchy

The page shall be organized in the following sequence.

## 1. Project Header

Contains:

- Project Name

- Short Description

- Project Health

- Current Phase

- Project Manager

- Sponsor

- Last Report Date

Purpose:

Provide immediate project identification and context.

## 2. Phase Timeline

A simplified Gantt containing project phases only.

The timeline occupies the full page width and becomes the primary visual representation of project progress.

Purpose:

Answer the question:

“Where are we in the project journey?”

## 3. Executive Summary

Subtitle:

Overall project status and current management focus.

Purpose:

Provide a concise narrative describing the current project situation.

This section is generated by AI and subsequently reviewed and approved by the Project Manager.

## 4. Delivery Status

Subtitle:

Current execution status of project delivery.

This section summarizes:

- Workstreams

- Milestones

- Overall Progress

The information is presented as compact executive cockpit indicators.

Purpose:

Answer:

“How is execution progressing?”

## 5. Attention

Subtitle:

Items currently requiring executive attention.

Displays:

- Open attention items

- Overdue items

- Escalated items

- Changes since previous report

Purpose:

Answer:

“What needs immediate attention?”

Selecting the card navigates directly to the operational Attention page.

## 6. Risks

Subtitle:

Current project exposure requiring monitoring or escalation.

Normal mode displays cockpit totals.

When escalated risks exist, the section automatically replaces summary counts with the highest priority risk description.

Purpose:

Answer:

“What could threaten project success?”

Selecting the section opens the Risk page.

## 7. Decisions

Subtitle:

Pending and escalated management decisions.

Normal mode displays cockpit totals.

When escalated decisions exist, the section displays the decision requiring immediate executive action.

Purpose:

Answer:

“Which decisions require management?”

Selecting the section opens the Decision page.

## 8. Project Pulse

Subtitle:

What has changed since the previous reporting period.

This section is fully system generated.

Examples:

- Completed workstreams

- Completed milestones

- Closed risks

- New escalations

- Schedule changes

Purpose:

Provide an objective operational summary of recent project movement.

## 9. Progress Since Last Report

Subtitle:

Major capabilities and business outcomes delivered during this reporting period.

This section replaces the previous “Achievements” concept.

Rather than listing completed workstreams or milestones individually, it summarizes meaningful project evolution.

Examples:

- Multilingual platform completed.

- Operational mobile workspace delivered.

- Time Tracking and Project Progress agents implemented.

- Natural Language implementation initiated.

The objective is to communicate business capability delivery rather than project administration activity.

This section is AI-generated and reviewed by the Project Manager.

## 10. Issues / Concerns

Subtitle:

Current concerns affecting project delivery.

Purpose:

Summarize issues requiring continued monitoring.

The narrative is generated from operational information and refined by the Project Manager.

## 11. Next Steps

Subtitle:

Planned activities for the next reporting period.

Generated from:

- Open workstreams

- Upcoming milestones

- Planned activities

Reviewed and edited by the Project Manager.

## 12. Management Ask

Subtitle:

Management decisions or support required.

Generated primarily from:

- Escalated decisions

- Escalated risks

- Resource constraints

- Budget exceptions

Reviewed and approved by the Project Manager.

## 13. Conclusion

Subtitle:

Overall project assessment.

Provides the final executive message regarding project direction.

AI-generated and reviewed by the Project Manager.

# Narrative Lifecycle

Narrative sections become managed business objects.

Each narrative follows the lifecycle:

Generate

↓

Review

↓

Edit

↓

Approve

↓

Operational data changes

↓

Daily Attention notification

↓

Generate updated proposal

Operational data always remains the system of record.

Narrative is the reviewed interpretation of that operational data.

# Daily Attention Integration

Narrative maintenance shall not clutter the Executive Briefing.

Instead, the Daily Attention workspace shall notify the Project Manager when operational changes indicate that one or more approved narrative sections may no longer reflect the current project status.

Examples:

- New completed milestones

- Newly escalated risks

- Approved decisions

- Significant schedule changes

The Project Manager reviews the proposed updated narrative before approval.

# Executive View vs Project Manager View

The Executive Briefing supports two presentation modes.

## Executive View

Displays only approved content.

No workflow information is visible.

No editing controls are available.

This view is used for:

- Executive consumption

- Steering Committees

- PDF export

- PowerPoint export

## Project Manager View

Displays the same layout while adding management controls.

Examples include:

- Generate proposal

- Review proposal

- Edit narrative

- Approve narrative

- Last approval date

- Last regeneration date

These management controls are visible only to users with appropriate permissions.

The Executive Briefing layout remains identical in both modes.

# Navigation

Every section acts as a navigation point to its corresponding operational page.

Examples:

- Delivery Status → Workstreams / Milestones

- Attention → Attention Workspace

- Risks → Risks

- Decisions → Decisions

The Executive Briefing becomes the entry point into detailed project management without duplicating operational functionality.

# Architectural Principles

The Executive Briefing shall remain an executive presentation layer over a single operational data model.

No business information shall be maintained separately for the Executive Briefing.

Operational entities remain the source of truth.

Narrative sections are AI-assisted summaries derived from those entities and remain fully editable and approvable by the Project Manager.

The objective is to minimize manual reporting effort while preserving complete Project Manager ownership of executive communication.