PROJECT OPERATIONS SYSTEM
RISK LIFECYCLE GOVERNANCE ARCHITECTURE
MASTER DESIGN DOCUMENT

Version: 1.0
Status: Approved Architecture
Purpose: Single Source of Truth for Risk Governance, Risk Reporting, Governance Review and Attention Intelligence

- EXECUTIVE SUMMARY

The Project Operations System shall evolve from a traditional risk register into a complete governance lifecycle management platform.

The objective is not only to identify and mitigate risks, but also to demonstrate:

- Risk identification

- Risk assessment

- Mitigation execution

- Evidence collection

- Residual risk evaluation

- Steering Committee review

- Formal risk closure

The architecture must support operational management, executive reporting, auditability and future agent-driven governance.

- ARCHITECTURAL PRINCIPLES

The following principles govern the design:

- Risks are governance entities.

- Mitigation actions are execution entities.

- Evidence proves execution.

- Residual assessments evaluate mitigation effectiveness.

- Steering Committees approve risk disposition.

- Risk closure requires governance approval.

- Lifecycle stages are derived, never manually maintained.

- Executive reporting derives from transactional facts.

- Governance itself should eventually become auditable.

- TARGET RISK LIFECYCLE

Risk Identified
↓
Inherent Risk Assessment
↓
Mitigation Actions Defined
↓
Mitigation Actions Executed
↓
Evidence Collected
↓
Residual Risk Assessment
↓
Committee Review
↓
Accept / Escalate / Continue Mitigation
↓
Risk Closure

- BUSINESS IDENTIFIERS

Risk

RI00001
RI00002
RI00003

Decision

DC00001
DC00002
DC00003

Risk Action

RA00001
RA00002
RA00003

- EXISTING ENTITIES RETAINED

ProjectRisk

Retain:

- riskCode

- title

- description

- owner

- category

- probability

- impact

- exposure

- status

ProjectRiskAction

Retain:

- actionCode

- title

- owner

- dueDate

- status

Existing governed status architecture remains valid.

Action completion does not imply risk reduction.

Action completion only proves execution.

- RISK ACTION ENHANCEMENTS

ProjectRiskAction

Add:

completionCriteria

Purpose:

Defines objective conditions required for completion.

Examples:

- Contract signed

- Audit passed

- UAT approved

- Validation completed

Completion criteria are planning statements.

Evidence provides proof.

- EVIDENCE MANAGEMENT

New Entity

RiskActionEvidence

Purpose:

Provide structured proof that mitigation actions have been implemented.

Fields

- id

- riskActionId

- evidenceTypeId

- title

- description

- documentReference

- url

- evidenceDate

- uploadedBy

- createdAt

Relationship

Risk
↓
Risk Action
↓
Evidence

Evidence belongs to mitigation actions.

Evidence is never attached directly to risks.

- EVIDENCE TYPES

New Master Data

EvidenceType

Initial Values

- DOCUMENT

- TEST_RESULT

- APPROVAL

- AUDIT_RECORD

- MEETING_MINUTES

- TRAINING_RECORD

- PHOTO

- SYSTEM_CONFIGURATION

- GO_LIVE_PROOF

- OTHER

- RISK ASSESSMENT

New Entity

RiskAssessment

Purpose

Maintain a complete audit trail of risk evolution.

Fields

- id

- riskId

- assessmentType

- probability

- impact

- exposure

- comments

- assessedBy

- assessmentDate

Assessment Types

- INHERENT

- RESIDUAL

Multiple assessments are allowed.

Example

Assessment 1

Type: INHERENT
Exposure: 20

Assessment 2

Type: RESIDUAL
Exposure: 12

Assessment 3

Type: RESIDUAL
Exposure: 6

This enables trend analysis and auditability.

- RESIDUAL ASSESSMENT

Residual assessments represent the Project Manager's proposed residual risk position.

The residual assessment is a recommendation.

It is not a governance decision.

Fields

- proposedProbability

- proposedImpact

- proposedExposure

- comments

Purpose

Provide input to Steering Committee review.

- COMMITTEE REVIEW

New Entity

RiskReview

Purpose

Capture Steering Committee governance decisions.

Fields

- id

- riskId

- residualAssessmentId

- reviewType

- reviewDate

- reviewedBy

- decision

- comments

Review Types

- INTERIM

- RESIDUAL

- CLOSURE

Review Decisions

- PENDING

- ACCEPTED

- CONTINUE_MITIGATION

- ESCALATED

- CLOSED

Multiple reviews are allowed.

Purpose

Preserve governance history.

- RISK CLOSURE RULES

A risk may only be closed when:

Rule 1

All active mitigation actions completed.

Rule 2

Required evidence exists.

Rule 3

Residual assessment exists.

Rule 4

Committee decision = CLOSED.

Only then may Risk Status become CLOSED.

- RISK LIFECYCLE SUMMARY

Purpose

Provide governance visibility.

One row per risk.

Columns

| Risk Description | Initial Exposure | Actions | Evidence | Residual Exposure | Committee Review | Lifecycle Stage |

Risk Description

Primary reporting identifier.

Risk code available for drill-down.

Initial Exposure

Display:

Exposure value + color.

Examples

🔴 20
🟠 12
🟢 4

Actions

completed / total

Examples

2/4
4/4

Evidence

provided / required

Examples

1/4
4/4

Residual Exposure

Blank until assessment exists.

Then:

🟢 4
🟠 8
🔴 15

Committee Review

Blank until eligible.

Then:

Pending
Accepted
Continue Mitigation
Escalated
Closed

Lifecycle Stage

Derived.

Never manually maintained.

- LIFECYCLE STAGE DERIVATION

Identified

Risk exists.
No mitigation actions.

Mitigation Planning

Actions defined.
Not started.

Mitigation Execution

Actions exist.
Not completed.

Evidence Collection

Actions complete.
Evidence incomplete.

Residual Assessment

Evidence complete.
Residual assessment missing.

Committee Review

Residual assessment complete.
Committee decision pending.

Closed

Committee approved closure.

Lifecycle Stage is calculated dynamically.

- EXECUTIVE RISK REVIEW PACK

Purpose

Provide Steering Committees with all information required to make governance decisions.

Applies to:

- Escalated Risks

- High Exposure Risks

- Risks requiring review

Section 1

Risk Overview

- Risk Code

- Description

- Owner

- Category

- Status

Section 2

Initial Assessment

- Probability

- Impact

- Exposure

Section 3

Current Situation

Narrative from PM.

Section 4

Mitigation Actions

- Action

- Owner

- Due Date

- Status

Section 5

Evidence

- Evidence

- Type

- Date

- Reference

Section 6

Proposed Residual Assessment

Prepared by PM.

Includes:

- Proposed Probability

- Proposed Impact

- Proposed Exposure

- Comments

Section 7

Risk Movement

Example

Initial Exposure: 20
Residual Exposure: 6

Risk Reduction: 70%

Section 8

Committee Decision

Reserved for Steering Committee.

Possible outcomes:

- Accept Residual Risk

- Continue Mitigation

- Escalate

- Close Risk

- DAILY ATTENTION WORKSPACE

New Workspace

/daily-attention

Purpose

Application-wide management-by-exception dashboard.

Not risk-specific.

Sections

Workstreams

- overdue

- delayed

- open beyond target date

Events / Milestones

- overdue

- incomplete

Risks

- high exposure

- missing mitigation actions

- missing evidence

- missing residual assessment

- awaiting committee review

Risk Actions

- overdue

- completed without evidence

Decisions

- open

- overdue

- awaiting approval

Reporting

- reporting pack overdue

- executive report refresh required

- ATTENTION AGENT FOUNDATION

The Attention Workspace becomes the foundation for future agents.

All future agents consume a common Attention Engine.

Phase 1

Attention Agent

Read-only.

Identifies issues.

Phase 2

Suggestion Agent

Creates recommendations.

Examples:

- Risk ready for residual assessment

- Risk ready for committee review

- Risk ready for closure

Phase 3

Operational Instruction Agent

Executes approved governance actions.

Phase 4

Voice Agent

Uses the same architecture through voice input.

Architectural Principle

There will not be separate agents for risks, milestones, workstreams, reporting and decisions.

All governance intelligence is centralized through the Attention Engine.

- FUTURE GOVERNANCE SESSION ARCHITECTURE

Status

Planned.
Not Phase 1.

Rationale

Mitigation Evidence proves:

"The action was performed."

Governance Review should eventually prove:

"The governance review occurred."

Future Entity

GovernanceReview

Possible Types

- Steering Committee

- Investment Committee

- Architecture Board

- Change Control Board

- Quality Review

Purpose

Store:

- discussion

- questions

- challenges

- requested actions

- decisions

- meeting minutes

Future Relationship

GovernanceReview
↓
RiskReview
DecisionReview
ChangeReview

This will allow complete auditability of governance activities without overcomplicating the first implementation phase.

- IMPLEMENTATION SEQUENCE

- Business code automation

- RiskAction completionCriteria

- EvidenceType master data

- RiskActionEvidence entity

- RiskAssessment entity

- RiskReview entity

- Risk closure rules

- Risk Lifecycle Summary

- Executive Risk Review Pack

- Daily Attention Workspace

- Attention Agent

- Suggestion Agent

- Operational Instruction Agent

- Voice Agent

- Governance Session Architecture

## END STATE

The Project Operations System provides complete traceability from:

Risk Identified
→ Mitigation Executed
→ Evidence Collected
→ Residual Risk Assessed
→ Steering Committee Decision
→ Risk Closed

while simultaneously creating the foundation for application-wide governance intelligence and future agent-driven project operations.